## Sheet1
Offline Sites under AOR by AKTI -- as of 2026-04-07
# | Site Code | Site Description | PLDT QID | LGU | Lot | Days Offline | Latest Status (MSMI Hashtag) | Last Update Info (Last 3 Updates only) | Next Action Owner | Last Updated Date | ¦ | ¦
1 | L4-011-00642 | Krus na Ligas Elementary School | 1-1G29K1Y | Quezon City | NCR | 1217 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-26¦MFM: ESA FR team conducted site visit on March 26, 2026 and their modem is up however AP is blinking red, for AKTI checking 2026-03-24¦MFM: ESA Provide a schedule for JT, Confirming For the site schedule from our team | AKTI | 13-Apr-2026¦Mon
2 | L4-005-00725 | Justo Lukban Elementary School | 1-1GK8105 | Manila City | NCR | 1217 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-26¦MFM: PLDT conducted standalone testing and their modem is up however Meraki dashboard still offline , for AKTI checking of AP at site 2026-03-24MFM: ESA Provide a schedule for JT, Confirming For the site schedule from our team | AKTI | 13-Apr-2026¦Mon
3 | L4-009-00731 | De Castro Elementary School | 1-1GQR8KF | Pasig City | NCR | 1217 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-26¦MFM: ESA team conducted site visit on MArch 26, 2026 and their modem is up however Meraki dashboard still offline , For AKTI checking of AP and bring New ap replacement 2026-03-24¦MFM: ESA Provide a schedule for JT, Confirming For the site schedule from our team | AKTI | 13-Apr-2026¦Mon
4 | L4-005-05881 | Philippine Normal University - Main |  | Manila City | NCR | 1095 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
5 | L4-015-06653 | Philippine International Convention Center |  | Pasay City | NCR | 700 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
6 | L4-005-00062 | National Commission for Culture and the Arts |  | Manila City | NCR | 670 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
7 | L4-008-00010 | Board of Investments |  | Makati City | NCR | 609 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
8 | L4-015-0004B | Overseas Workers Welfare Administration |  | Pasay City | NCR | 609 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
9 | L4-005-00016 | Bureau of the Treasury |  | Manila City | NCR | 578 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
10 | L4-011-0002F | Social Security System |  | Quezon City | NCR | 578 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for replacement of ISR 2026-03-25¦Akti: Defective ISR 2026-03-13¦ BSV: An email was submitted to DICT. | AKTI | 13-Apr-2026¦Mon
11 | L4-004-05E8A | CAA-D Health Center | 1-1GX2UMS | Las Piñas City | NCR | 548 | #SLA-4SiteRelocation | 2026-03-19¦MFM: This site is for relocation of equipment in new building. Called site coordinator and they agreed to relocate the combox to the new building. For AKTI schedule for the relocation. 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-05¦MFM: Sent an email to PLDT esa regarding los issue and sent also and email to DICT for trasfer equipment in new building (Lanzones St. Phase 2), Sent an email to DICT for relocation of the equipment | AKTI DICT | 19-Mar-2026¦Thu
12 | L4-011-00064 | National Anti-Poverty Commission |  | Quezon City | NCR | 548 | #SLA-iGov-DownCMS | 2026-04-07 ¦ MFM: Sir Ronald found the AP at old building, AP is kept by sir ronald now at his office 2026-04-01 ¦ MFM: Called the Site Coordinator regarding the missing AP (M33) and requested to check the AP in the old building; he advised that he will visit the site after Holy Week. 2026-03-25¦MFM:Agenct has been relocated. AP is missing | AKTI | 07-Apr-2026¦Tue
13 | L4-011-00047 | Philippine Atmospheric, Geophysical and Astronomical Services Administration |  | Quezon City | NCR | 548 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: An email was submitted to DICT. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 13-Apr-2026¦Mon
14 | L4-011-00088 | Commission on Audit |  | Quezon City | NCR | 548 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: An email was submitted to DICT. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 13-Apr-2026¦Mon
15 | L4-011-05F61 | Masambong Health Center | 1-1H9YMIL | Quezon City | NCR | 518 | #SLA-4SiteRelocation | 2026-04-06¦MFM:The Site Coordinator requested to relocate the Combox to another area to improve signal reception, as the current location is unable to receive a stable signal.Sent and email to DICT regarding for relocation of the combox and sent an email to PLDT esam regarding no internet connection 2026-03-26¦AKTI:Modem issue is no internet connection 2026-03-19¦ MFM: Subject For site inspection and requesting AKTI to provide status of the modem and proof of no internet connection | PLDT ESAM AKTI DICT | 06-Apr-2026¦Mon
16 | L4-005-0006D | Intramuros Administration |  | Manila City | NCR | 518 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 13-Apr-2026¦Mon
17 | L4-011-00623 | Camarilla Elementary School | 1-1FZTPV9 | Quezon City | NCR | 487 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-19¦MFM: As per PLDT esa the modem was up on their end, Will Dispatch a team and provide updates during site inspection, For AKTI checking 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
18 | L4-011-00643 | San Jose Elementary School - Pag-Ibig sa Nayon Annex | 1-1G2CU9R | Quezon City | NCR | 457 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-17¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-02¦MFM: Per PLDT , This was attended by our field engineer last Feb, 11 2026, conduct re-routing of fiber cable, replaced connector at fiber box and replaced defective modem. Standalone testing was found ok. please check the cable connected to our AP and also check power injector and AP Itself . . | AKTI | 13-Apr-2026¦Mon
19 | L4-003-063CE | Barangay 14 Health Center | 1-1HA0Z3W | Caloocan City | NCR | 457 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-19¦ MFM:Subject For site inspection and requesting AKTI to provide status of the modem and proof of no internet connection 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
20 | L4-005-0007D | Department of Finance |  | Manila City | NCR | 457 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-06¦MFM: Sent a message in TG to Akti for restoration 2026-02-12¦MFM: Site offline, For AKTI checking | AKTI | 13-Apr-2026¦Mon
21 | L4-011-00044 | Philippine Coconut Authority |  | Quezon City | NCR | 457 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for replacement of ISR 2026-03-25¦Akti: Defective ISR 2026-03-13¦ BSV: An email was submitted to DICT. | AKTI | 13-Apr-2026¦Mon
22 | L4-005-04D9A | Carlos P. Garcia High School | 1-1G975XW | Manila City | NCR | 396 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: As per PLDT, 50 m of FOC was provided for replacement We contacted the site coordinator to confirm the availability of the FOC cable, and it was confirmed that the cable is already on-site. For AKTI checking and restoration. 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
23 | L4-006-0076F | Kalumpang Elementary School | 1-1FYAD1A | Marikina City | NCR | 396 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: As per PLDT, during their standalone testing modem was up, For AKTI checking 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
24 | L4-005-00763 | Legarda Elementary School | 1-1GXIHHZ | Manila City | NCR | 365 | #SLA-4SiteRelocation | 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT 2026-02-10¦MFM- The site is requesting the relocation of the Commbox and modem to a more visible and accessible area, and also the repair of the cut wire at the site. | AKTI | 16-Mar-2026¦Mon
25 | L4-005-06650 | Pamantasan ng Lungsod ng Maynila |  | Manila City | NCR | 365 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦ BSV: An email was submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
26 | L4-009-0070B | Pineda Elementary School | 1-1GQR8DD | Pasig City | NCR | 341 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-17¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
27 | L4-012-007EF | Paltok Elementary School | 1-1G5H83I | Valenzuela City | NCR | 320 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: AS per PLDT, Modem is always UP in their end , For AKTi checking . Please check AP if neccessary or Direct to connect via laptop 2026-02-26¦MFM: Sent an email to PLDT providing latest modem status , there still no internet connection | AKTI | 13-Apr-2026¦Mon
28 | L4-022-00009 | Department of Science and Technology |  | Taguig City | NCR | 320 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 13-Apr-2026¦Mon
29 | L4-007-05FA3 | Niugan Health Center | 1-1G0UATB | Malabon City | NCR | 317 | #SLA-ExtDependency | 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-15¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | DICT AKTI | 16-Mar-2026¦Mon
30 | L4-011-00662 | Commonwealth Elementary School | 1-1FZ29GU | Quezon City | NCR | 311 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: Per PLDT, Modem Is UP on their end , FR found out that that AP is not working , for AKTI AP replacement 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
31 | L4-011-05978 | Pinaglabanan Shrine | 169537192800001 | San Juan City | NCR | 308 | #SLA-CMS_Down | 2026-04-07¦MFM: For new AP replacement 2026-03-12¦MFM: AKTI conducted site inspection at site and found out that the AP is defective, For new AP replacement 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 07-Apr-2026¦Tue
32 | L4-011-05F53 | Frisco Health Center | 1-1G621UN | Quezon City | NCR | 277 | #SLA-ExtDependency | 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-02¦MFM: AKTI conducted a site inspection and found that the equipment is missing; the site coordinator mentioned that the Combox is located in the old building, but AKTI was unable to locate it in the said area. 2026-02-26¦MFM: PLDt esa requesting modem status at site , Subject for site inspection by AKTI | SITE AKTI | 16-Mar-2026¦Mon
33 | L4-003-05F88 | Barangay 12 Health Center | 1-1G7IUXI | Caloocan City | NCR | 259 | #SLA-CMS_Down | 2026-04-07¦MFM- For AKTI site inspection and to check the power issue 2026-03-04¦MFM- Sent a follow up message to AKTI in TG. Requesting to check their Power issue 2025-12-22¦JCR- Sent a message to AKTI in TG. Requesting to check their Power issue | AKTI | 07-Apr-2026¦Tue
34 | L4-005-05E6D | Unang Sigaw Barangay Hall | 169537191863152 | Quezon City | NCR | 256 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: AS per PLDT, STandalone testing for Modem is successful on their end , For AKTi checking . Please check AP if neccessary or Direct to connect via laptop 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
35 | L4-009-06658 | Deparment of Social Welfare and Development - Manila City | 169537208777948 | Manila City | NCR | 247 | #SLA-ExtDependency | 2026-02-25¦AMM:Email sent to PLDT ESA and DICT 2026-01-07¦JCR- Sent a follow up message to AKTI in TG regarding the relocation 2025-12-12¦JCR- Sent a follow up email to AKTI in TG regarding the issue | AKTI | 25-Feb-2026¦Wed
36 | L4-011-0008B | Bureau of Jail Management and Penology |  | Quezon City | NCR | 226 | #SLA-iGov-DownCMS | 2026-04-08¦ MFM: As per AKTI, ICT coordinator is on leave , for AKTI rescheduling 2026-03-13¦ BSV: An email was submitted to DICT. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 08-Apr-2026¦Wed
37 | L4-013-00007 | National Commission on Muslim Filipinos | 169537148790671 | Quezon City | NCR | 219 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-04¦MFM: per PLDT esa, upon checking monitored able to ping WAN IP, for AKTI checking 2026-03-03¦MFM: Sent an email to PLDT providing modem status at site | AKTI | 13-Apr-2026¦Mon
38 | L4-00A-05FB5 | Tangos Health Center | 1-1HA6VJA | Navotas City | NCR | 216 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: AS per PLDT, Modem is always UP in the end , For AKTI checking . Please check AP if neccessary or Direct to connect via laptop 2026-03-17¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
39 | L4-007-007C2 | Bagong Lote Elementary School | 1-1G0PGYS | Malabon City | NCR | 213 | #SLA-ExtDependency | 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-25¦AKTI: For relocation waiting for approval of the school 2026-02-20¦MFM- Per PLDT. Modem is UP on their side , Upon checking of PLDT theres no power cables that connected to combox and also no power source , for AKTI checking | DICT AKTI | 16-Mar-2026¦Mon
40 | L4-013-006BC | Sto. Niño Elementary School | 1-1G8UMPA | Parañaque City | NCR | 198 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-02¦MFM: Per PLDT, Modem is monitored non-alarm. However, no equipment connected to LAN 2 of their Huawei modem., for AKTI checking | AKTI | 13-Apr-2026¦Mon
41 | L4-005-00045 | Philippine Coast Guard |  | Manila City | NCR | 195 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-24¦AMM: Sent an email to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
42 | L4-004-08322 | Navotas City Hall | 169537197878708 | Navotas City | NCR | 192 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: For AKTI checking. Please check AP if neccessary or Direct to connect via laptop 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
43 | L4-006-05F0E | Concepcion Dos Health Center | 1-1G0M9JJ | Marikina City | NCR | 189 | #SLA-ExtDependency | 2026-03-16¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-04¦MFM: Sent a follow up message to AKTI regarding the relocation of equipment to the new building 2026-01-05¦JCR- Sent a follow up message to AKTI in TG regarding the site location | DICT AKTI | 16-Mar-2026¦Mon
44 | L4-008-00012 | Metropolitan Manila Development Authority |  | Makati City | NCR | 186 | #CMS-ForTransfer | 2026-03-12¦MFM: Subejct for AKTI reco of site transfer. Igov site. 2026-02-01¦ RJA: Subejct for AKTI reco of site transfer. Igov site. Once with reco, subejct for MDS req to DICT for the installation 2025-12-12¦JCR- Due to infeasibility of the AP location request by site coordinator site will now be requested for transfer with DICT | AKTI | 12-Mar-2026¦Thu
45 | L4-009-00704 | Liberato Damian Elementary School | 1-1GVZ1IU | Pasig City | NCR | 186 | #SLA-CMS_Down | 2026-04-07¦MFM:To restore - for schedule from AKTI 2026-02-25¦AMM:Email sent to PLDT ESA and DICT 2026-02-16¦RBD : Sent an email to PLDT to check for the downtime | AKTI | 07-Apr-2026¦Tue
46 | L4-013-05EC0 | BF Homes Health Center | 1-1G96P6L | Parañaque City | NCR | 174 | #SLA-ExtDependency | 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-24¦AMM- Sent an email to PLDT ESA and DICT 2025-12-18¦JCR- Sent an email to DICT regarding the Renovation of the site | AKTI | 13-Mar-2026¦Fri
47 | L4-009-05F1E | Bagong Katipunan | 1-1H874P3 | Pasig City | NCR | 156 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-26¦MFM- Per PLDT esa, PLDT side is tested okay but no connection when extended to our equipment. For AKTI checking | AKTI | 13-Apr-2026¦Mon
48 | L4-005-00711 | Aurora A. Quezon Elementary School | 1-1GK7M8C | Manila City | NCR | 146 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: For AKTI checking. Please check AP if neccessary or Direct to connect via laptop 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
49 | L4-008-049FA | Bangkal High School | 1-1GEEMXU | Makati City | NCR | 134 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦MFM: Maam fatima requesting JT on february 9, 2026, Please check on your end for clarification. Our team will be dispatch for site inspection. 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
50 | L4-011-00638 | Batino Elementary School - SPED Center | 1-1G1WS2P | Quezon City | NCR | 131 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-09¦MFM: Contact person is unreachable , for AKTI site inspection | AKTI | 13-Apr-2026¦Mon
51 | L4-003-04D56 | Manuel L. Quezon High School | 1-1FUXW3T | Caloocan City | NCR | 131 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: As per ESAm, their Team replaced the FOC at NAP , For AKTI checking 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
52 | L4-011-05F51 | Escopa Health Center | 1-1G60XET | Quezon City | NCR | 131 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: Our team conducted site inspection last December 23, 2025 and found that the Modem is LOS, Ma’am Fatima requested joint testing on February 9, 2026. Kindly check on your end for clarification. Our Team will dispatch for site inspection 2026-03-13¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
53 | L4-011-04A15 | Dona Rosario High School | 1-1G80C24 | Quezon City | NCR | 125 | #SLA-CMS_Down | 2026-04-10¦MFM: Site is offline in meraki dashboard , for AKTI checking 2026-03-16¦AKTI:Site is online 2026-03-06¦MFM: STRLNK Activated however still offline in meraki dashboard , for AKTI checking | AKTI | 10-Apr-2026¦Fri
54 | L4-005-0006C | Land Bank of the Philippines |  | Manila City | NCR | 122 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-02¦MFM: Site is offline , for AKTI checking 2025-01-06¦JGT: site online | AKTI | 13-Apr-2026¦Mon
55 | L4-005-00191 | San Lazaro Hospital |  | Manila City | NCR | 122 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-02-25¦AMM:Email sent to PLDT ESA and DICT 2026-02-12¦¦MFM: Site offline, For AKTI checking | AKTI | 13-Apr-2026¦Mon
56 | L4-011-00052 | National Power Corporation |  | Quezon City | NCR | 122 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-02¦MFM: Site is offline , for AKTI checking 2024-12-13¦JGT: site online on Dec 10, 2024 | AKTI | 13-Apr-2026¦Mon
57 | L4-005-05E66 | Pasong Tamo Barangay Hall | 169537149851801 | Quezon City | NCR | 122 | #SLA-ExtDependency | 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-04¦MFM:Called the site coordinator, who mentioned that the site is still under construction with no estimated completion date yet, as demolition has just started, The combox equipment has been set aside by the workers on site. 2026-03-03¦MFM: Per AKTI, Site is for relocation and ongoing under Construction, Sent an email to DICT regarding the issue | AKTI SITE | 27-Mar-2026¦Fri
58 | L4-05B-00A60 | Pagudpud Central Elementary School | 1-1GS1RXF | Pagudpud | Ilocos Norte | 116 | #SLA-CMS_Down | 2026-04-07¦MFM- PLDT FR conducted standalone testing and modem is up on their end however in meraki dashboard still offline, FR mentiuoned that Ap led is blinking, for AKTI checking 2026-04-01¦MFM- PLDT conducted activity at site and report that they will endorse to their fiber team for checking outside the cable 2026-03-23¦MFM- Sent an email providing Latest modem and inform them that the fiber Cable have a cut and need for checking on their end | AKTI | 07-Apr-2026¦Tue
59 | L4-011-0006B | Land Registration Authority |  | Quezon City | NCR | 116 | #SLA-iGov-DownCMS | 2026-03-30¦AKTI:AP no power, waiting for the advise of site coordinator for accessing the server 2026-02-25¦AMM:Email sent to PLDT ESA and DICT 2026-02-12¦¦MFM: Site offline, For AKTI checking | AKTI | 30-Mar-2026¦Mon
60 | L4-005-0006E | Insurance Commission |  | Manila City | NCR | 116 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-06¦MFM: Sent a message in TG to Akti for restoration 2026-02-12¦MFM: Site offline, For AKTI checking | AKTI | 22-Mar-2026¦Sun
61 | L4-015-00093 | Anti-Money Laundering Council |  | Manila City | NCR | 116 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-02¦MFM: Site is offline , for AKTI checking 2026-01-30¦RBD: There is no downtime occurring during the specified period. Not subjected to rebates | AKTI | 13-Apr-2026¦Mon
62 | L4-011-00176 | Philippine Heart Center |  | Quezon City | NCR | 107 | #SLA-ExtDependency | 2026-03-03¦AKTI: Site is for relocation and ongoing under C0nstruction 2026-02-23¦MFM- Site is offline , for AKTI checking 2026-01-09¦JCR- As per JPC they successfully install the new media con and make sure before they leave that the connection is stable. But after few days the site is down. For MDS Checking and restoration | AKTI DICT | 03-Mar-2026¦Tue
63 | L4-011-0063B | Pinyahan Elementary School | 1-1G1WL33 | Quezon City | NCR | 104 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-24¦ MFM: As per ESAM, their Team replaced the FOC at NAP , For AKTI checking 2026-03-02¦MFM: Sent a follow email regarding the issue | AKTI | 13-Apr-2026¦Mon
64 | L4-022-0598B | Pamantasan ng Lungsod ng Valenzuela - Annex | 169537165798443 | Valenzuela City | NCR | 92 | #SLA-ExtrnlDep/NoPower | 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-12¦MFM: For AKTI checking regarding the status of the power at site 2026-02-25¦AKTI:Power issue the school electrician will fix the wire to the main power panel box as per advice of the site coordinator | AKTI | 27-Mar-2026¦Fri
65 | L4-012-05FCE | Manotok Health Center | 1-1G9LL7D | Valenzuela City | NCR | 89 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-24¦MFM: As per ESA, no LAN cable connected to LAN 2, for AKTI checking | AKTI | 13-Apr-2026¦Mon
66 | L4-014-063BD | Progreso Barangay Hall | 1-1FYC3NG | San Juan City | NCR | 70 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: As per ESAM Modem Is up on their end however in meraki still offline , For AKTI checking 2026-03-02¦MFM: Sent an email to PLDT esa informing that the service order is closed | AKTI | 13-Apr-2026¦Mon
67 | L4-012-05FBE | Canumay East Health Center | 1-1G9JLOK | Valenzuela City | NCR | 69 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: As per ESAM, Their Team replaced FIC at NAP, for AKTI checking 2026-03-10¦MFM: Sent an email to PLDT esa regarding LOS issue | AKTI | 13-Apr-2026¦Mon
68 | L4-008-006E7 | Hen. Pio del Pilar Elementary School - Main | 1-1G9WWQJ | Makati City | NCR | 67 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: As per ESAM, no LAN cable connected to LAN 2, for AKTI checking 2026-02-26¦MFM: Sent an email to PLDT esa regarding LOS issue | AKTI | 13-Apr-2026¦Mon
69 | L4-004-06651 | Marikina City Hall | 169537150886616 | Marikina City | NCR | 66 | #SLA-CMS_Down | 2026-04-06¦MFM: As per PLDT, Signal at site is UP adn modem is accessible, for AKTI checking 2026-04-01¦MFM: Sent an email to PLDT regarding LOS issue 2026-03-25¦AKTI:Modem issue is blinking LOS | AKTI | 06-Apr-2026¦Mon
70 | L4-009-00189 | Rizal Medical Center | 1-1HBFIPF | Pasig City | NCR | 61 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-06¦MFM: Sent a message in TG to Akti for restoration 2026-02-16¦MFM: Site is offline since feb 11, 2026, for AKTI checking | AKTI PLDT ESAM | 07-Apr-2026¦Tue
71 | L4-013-049F5 | Baclaran National High School | 1-1G8F7C3 | Parañaque City | NCR | 56 | #SLA-ExtDependency | 2026-03-13¦RBD:Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-05¦MFM: Site coordinator requesting to relocate the equipment to new building , sent an email to DICT regarding relocation of the equipment, Additonally, the modem has no power becuase it needs to installed first at the lobby 2026-03-02¦AKTI:Modem issue is blinking LOS. Request for transfer to new PNHS baclaran Annex Senior HS building. ( new address Dimasalang extension Baraclran -Paranaque) | DICT AKTI | 13-Mar-2026¦Fri
72 | L4-015-06654 | Cultural Center of the Philippines - Administrative Office |  | Pasay City | NCR | 53 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-16¦MFM: Site is offline, for AKTI checking 2026-03-15¦RBD:Sent an email to DICT for the downtime. | AKTI | 13-Apr-2026¦Mon
73 | L4-022-006B9 | Ricardo P. Cruz Sr. Elementary School | 1-1H90MT5 | Taguig City | NCR | 49 | #SLA-CMS_Down | 2026-03-23¦Akti: MDS to provide AP 2026-03-23¦MFM: AKTi found that the AP is defective , for AP replacement 2026-03-22¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | AKTI MDS | 23-Mar-2026¦Mon
74 | L4-003-05893 | University of Caloocan City - Camarin Business Campus | 1-1G74ZN8 | Caloocan City | NCR | 48 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-16¦MFM: Site is offline, for AKTI checking 2026-03-02¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT | AKTI PLDT ESAM | 07-Apr-2026¦Tue
75 | L4-005-00079 | Department of Public Works and Highways |  | Manila City | NCR | 38 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-10¦RBD:Sent an email to DICT for the downtime. 2026-03-02¦MFM: Site is offline since feb 25, 2026 , for AKTI checking | AKTI | 13-Apr-2026¦Mon
76 | L4-007-007AF | Epifanio de los Santos Elementary School | 1-1G0NON9 | Malabon City | NCR | 37 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: As per ESAm, Their team replaced the FIC at Nap, Modem is up. For AKTi checking 2026-03-16¦MFM: Sent an email to PLDT esa regarding LOS issue | AKTI | 13-Apr-2026¦Mon
77 | L4-012-007EC | Isla Elementary School | 1-1G3BMD0 | Valenzuela City | NCR | 37 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: Our team did not receive email that the circuit is now up, Upon checking in meraki the site still offline , For AKTI checking 2026-03-16¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
78 | L4-014-00190 | San Juan Medical Center | 1-1FY9RSW | San Juan City | NCR | 37 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-10¦MFM: Site is oflline on march 7, 2026, for AKTI checking 2025-01-06¦JGT: site online | AKTI PLDT ESAM | 07-Apr-2026¦Tue
79 | L4-009-05F38 | Sagad Health Center | 1-1GOYOF1 | Pasig City | NCR | 35 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-03¦RBD:Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2025-06-02¦JCR- The modem is off, JPC turn on and restart the Modem. The site regained its connectivity. The doctor want to relocate the combox inside of thefacility | AKTI PLDT ESAM | 07-Apr-2026¦Tue
80 | L4-007-05F9E | Hulong Duhat Health Center | 1-1G0TGOM | Malabon City | NCR | 35 | #CMS-ForTransfer | 2026-03-16¦AKTI:Site is for relocation to new building 2026-03-12¦MFM- Site is offline since march 9, 2026, for AKTI checking 2026-02-16¦AMM : Email sent to PLDT for checking for downtime and send email to DICT | AKTI | 16-Mar-2026¦Mon
81 | L4-003-04D5C | Sampaguita High School | 1-1FUPQ9D | Caloocan City | NCR | 34 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-16¦MFM: Site is offline since March 10, 2026 for AKTI checking 2026-02-02¦AMM: Manual ticket created | AKTI PLDT ESAM | 07-Apr-2026¦Tue
82 | L4-011-00636 | Project 3 Elementary School | 1-1G1VZW7 | Quezon City | NCR | 33 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-16¦MFM: Site is offline since March 11, 2026, for AKTI checking 2026-03-11¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | PLDT ESAM AKTI | 07-Apr-2026¦Tue
83 | L4-005-04D98 | Manila Science High School | 1-1G8WCF3 | Manila City | NCR | 32 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-22¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2026-03-12¦MFM: AKTI restarted the modem and it went online, but after an hour it went offline again | AKTI | 13-Apr-2026¦Mon
84 | L4-015-05ED2 | Dona Marta Health Center | 1-1GEFJXY | Pasay City | NCR | 31 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-31¦MFM: As per ESAM, Upon checking the modem is off , for AKTI checking 2026-03-22¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
85 | L4-011-05F58 | Holy Spirit Health Center | 1-1G6227R | Quezon City | NCR | 31 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Requesting ESAM to check if the modem is reachable on their end 2026-03-16¦MFM: Site is offline since March 13, 2026 for AKTI checking 2026-03-02¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT | AKTI PLDT ESAM | 07-Apr-2026¦Tue
86 | L4-005-0071D | Fernando Ma. Guerrero Elementary School | 1-1GK7MEO | Manila City | NCR | 30 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2026-02-20¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2025-09-04¦MFM: Site is online | PLDT ESAM AKTI | 07-Apr-2026¦Tue
87 | L4-007-007A7 | Ninoy Aquino Elementary School | 1-1G0N6XB | Malabon City | NCR | 30 | #CMS-4Restore-AP | 2026-03-26¦AKTI:No power AP (DEFECTIVE) 2026-03-16¦MFM: Site is offline since March 13, 2026, for AKTI checking 2026-03-15¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. | AKTI | 26-Mar-2026¦Thu
88 | L4-013-006C7 | Tambo Elementary School | 1-1G96OOF | Parañaque City | NCR | 28 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2025-11-19¦MFM: Done rectified by PLDT ESAM , Site regained its connectivity 2025-08-28¦JCR: sent follow up email to PLDT-ESAM | PLDT ESAM AKTI | 07-Apr-2026¦Tue
89 | L4-008-04D3B | San Isidro National High School | 1-1GEG1HM | Makati City | NCR | 26 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2026-03-23¦AMM:Email sent to PLDT ESA and DICT 2026-03-16¦AMM:Email sent to PLDT ESA and DICT | PLDT ESAM AKTI | 07-Apr-2026¦Tue
90 | L4-012-04D15 | Caruhatan National High School | 1-1G0DJUA | Valenzuela City | NCR | 26 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-25¦MFM: AS per ESA, Their team replaced the modem however they found out that AP is defective , for AP replacement 2026-03-11¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
91 | L4-011-04D79 | New Era High School | 1-1H9YMZD | Quezon City | NCR | 25 | #SLA-CMS_Down | 2026-03-23¦Akti MDS to provide AP 2026-03-19¦AKTI:No SSID detected after performing hard reset and replacing cable still no SSID. I"ll just go back to replace AP. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI MDS | 23-Mar-2026¦Mon
92 | L4-005-00751 | Gen. L. Geronimo Elementary School | 1-1HJ9TDH | Manila City | NCR | 25 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2024-07-12¦JGT: modem installed by PLDT, link acceptance done by MDS and PLDT 2024-07-01¦JGT: sent email to PLDT in regards to their pending deliverables | PLDT ESAM AKTI | 07-Apr-2026¦Tue
93 | L4-011-04D73 | Don Quintin Paredes High School | 1-1G83J65 | Quezon City | NCR | 24 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-09¦MFM: Site is now online on Mar 9, 2026 | PLDT ESAM AKTI | 07-Apr-2026¦Tue
94 | L4-006-04D3E | Parang High School | 1-1FY6G0O | Marikina City | NCR | 24 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline, requesting ESAM to check if the modem is reachable on their end 2026-03-04¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2025-01-06¦JGT: site online | PLDT ESAM AKTI | 07-Apr-2026¦Tue
95 | L4-043-0666D | SUYO NATIONAL HIGH SCHOOL | 169209171977960 / 169537141499089 | Dingras | Ilocos Norte | 17 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on March 27 2026, for AKTI chceking 2026-03-26¦AMM:Email sent to PLDT ESA and DICT 2026-03-03¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 07-Apr-2026¦Tue
96 | L4-00B-049DA | Muntinlupa National High School - NBP Annex | 1-1H70K1Z | Muntinlupa City | NCR | 16 | #SLA-CMS-ForAcceptance | 2026-02-24¦MFM: Site is now online 2026-01-23¦JCR- As per AKTI that they installed the starlink and the CMS and LINK Accepted on December 10, 2025 2025-12-10¦AKTI: For Starlink Activation / inslallation / acceptance | AKTI | 24-Feb-2026¦Tue
97 | L4-012-05FD6 | Parada Health Center | 1-1GB9B0M | Valenzuela City | NCR | 16 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-31¦MFM: Site is Offline since March 27, 2026 for AKTi checking 2026-03-19¦MFM: Site is now online on March 19, 2026 | AKTI | 13-Apr-2026¦Mon
98 | L4-006-05F19 | Santa Elena Health Center | 1-1G0MD0L | Marikina City | NCR | 16 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-31¦MFM: Site is Offline since march 28, 2026 for AKTi checking 2025-01-06¦JGT: site online | AKTI | 13-Apr-2026¦Mon
99 | L4-13F-010C6 | Samal North ES | 169105171042017 | Samal | Bataan | 15 | #SLA-CMS_Down | 2026-04-07¦AMM:Email sent to PLDT ESA and DICT 2026-04-06¦AMM:Email sent to PLDT ESA and DICT 2026-04-01¦MFM: Site is offline On March 29, 2026 , for AKTI checking | AKTI | 07-Apr-2026¦Tue
100 | L4-027-05DEC | Bacarra MHO | 167600179490765 / 169537147564891 | Bacarra | Ilocos Norte | 15 | #SLA-CMS_Down | 2026-04-13¦AMM:Email sent to PLDT ESA and DICT 2026-04-07 ¦MFM: Site is offline on March 28 2026, for AKTI chceking 2026-03-24¦AMM:Email sent to PLDT ESA and DICT | AKTI | 13-Apr-2026¦Mon
101 | L4-011-00109 | East Avenue Medical Center |  | Quezon City | NCR | 15 | #SLA-iGov-DownCMS | 2026-04-07 ¦MFM: Site is offline , for AKTI checking 2026-03-12¦MFM: Site is now online 2026-02-12¦¦MFM: Site offline, For AKTI checking | AKTI | 07-Apr-2026¦Tue
102 | L4-11F-06D32 | Carbonel ES | 169104187996503 | Gerona | Tarlac | 14 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on March 30, 2026, for AKTI chceking 2026-03-26¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-25¦Akti: Reset modem | AKTI | 07-Apr-2026¦Tue
103 | L4-007-049E0 | Tañong Integrated School | 1-1G0AO7S | Malabon City | NCR | 14 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since March 30, 2026, For AKTI checking 2026-03-30¦MFM: Site is now online on March 29, 2026 2026-03-27¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. | AKTI | 10-Apr-2026¦Fri
104 | L4-011-04D6C | Camp Crame High School | 1-1G82H2C | Quezon City | NCR | 13 | #SLA-CMS_Down | 2026-04-10¦MFM: Site is offline since March 31, 2026, for AKTI checking 2026-03-22¦RBD:Sent an email to DICT for the downtime. 2026-03-21¦RBD:Sent an email to DICT for the downtime. | AKTI | 10-Apr-2026¦Fri
105 | L4-063-00A35 | Pasuquin Central Elementary School | 169209130842864 | Pasuquin | Ilocos Norte | 13 | #SLA-CMS_Down | 2026-04-10¦AMM:Email sent to PLDT ESA and DICT 2026-04-10¦MFM:Site is offline since March 31, 2026, for AKTI checking 2026-04-07¦AMM:Email sent to PLDT ESA and DICT | AKTI | 10-Apr-2026¦Fri
106 | L4-12B-011C3 | San Jose ES | 172697123947300 | Mayantoc | Tarlac | 13 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on March 31, 2026, for AKTI chceking 2026-03-26¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-25¦Akti: Reset modem | AKTI | 07-Apr-2026¦Tue
107 | L4-022-0644C | Philippine Economic Zone Authority | 169537188872769 | Pasay City | NCR | 12 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on April 1, 2026, for AKTI checking 2025-11-26¦JCR- Done CMS acceptance on November 26, 2025 2025-11-07¦JCR- Sent a follow up message to AKTI in TG | AKTI | 07-Apr-2026¦Tue
108 | L4-003-04A0B | Kasarinlan High School | 1-1G73DS3 | Caloocan City | NCR | 12 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on march 31, 2026 , for AKTI checking 2026-03-20¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-16¦AMM:Email sent to PLDT ESA and DICT | AKTI | 07-Apr-2026¦Tue
109 | L4-003-04D59 | Amparo High School | 1-1FUQAVZ | Caloocan City | NCR | 11 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 2, 2026, For AKTI checking 2026-03-29¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2026-03-22¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | AKTI | 10-Apr-2026¦Fri
110 | L4-011-00031 | National Defense College of the Philippines |  | Quezon City | NCR | 11 | #SLA-iGov-DownCMS | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-06¦MFM: Sent a message in TG to Akti for restoration 2026-02-18¦RBD : Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT | AKTI | 13-Apr-2026¦Mon
111 | L4-003-0078B | San Jose Elementary School - Annex | 1-1H99C62 | Caloocan City | NCR | 8 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on April 4, 2026,for AKTI checking 2026-02-25¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2026-02-04¦MFM: Site online on feb 3, 2026 | AKTI | 07-Apr-2026¦Tue
112 | L4-063-00A32 | Madalayap Elementary School | 169209120839821 | Pasuquin | Ilocos Norte | 7 | #SLA-CMS_Down | 2026-04-07¦ MFM: Site is offline on April 6, 2026, for AKTI checking 2026-03-18¦ MFM: Done rectiifed by AKTI, site is now online on Mar 17, 2026 2026-03-03¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 07-Apr-2026¦Tue
113 | L4-05B-0499F | Pagudpud NHS | 1-1GS2IMI | Pagudpud | Ilocos Norte | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 7, 2026, For AKTI checking 2026-03-23¦MFM: Site is online, Team will observe the connectivity and coordinate with the site coordinator, especially with the upcoming summer break, to ensure stable and continuous connectivity. 2026-03-18¦Akti: They unplug the power from the source because their reason is they cannot use the freewifi due to weak internet signal. | AKTI | 10-Apr-2026¦Fri
114 | L4-012-007F4 | Canumay East Elementary School | 1-1G6EL9Q | Valenzuela City | NCR | 7 | #SLA-CMS_Down | 2026-04-10¦MFM: Site is offline since April 6, 2026, for AKTI checking 2026-04-01¦MFM: Site is now online on MArch 31, 2026 2026-03-31¦MFM: Site is Offline since March 31, 2026 for AKTi checking | AKTI | 10-Apr-2026¦Fri
115 | L4-137-06D91 | Manaois Elementary School | 1-1GEH2BV | Paniqui | Tarlac | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 6, 2026, For AKTI checking 2026-03-25¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2025-12-22¦JCR: The site is online on December 21 2025 | AKTI | 10-Apr-2026¦Fri
116 | L4-007-007B9 | Catmon Integrated School | 1-1G0O9DW | Malabon City | NCR | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 6, 2026, For AKTI checking 2026-03-18¦MFM: Site is now online on march 18, 2026 2026-02-25¦AMM:Email sent to PLDT ESA and DICT | AKTI | 10-Apr-2026¦Fri
117 | L4-004-049F2 | Las Piñas East National High School - Equitable Annex | 1-1GT2K0C | Las Piñas City | NCR | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 6, 2026, For AKTI checking 2026-02-10¦AMM: Email sent to PLDT and DICT 2026-01-19¦ AMM - Ticket request sent | AKTI | 10-Apr-2026¦Fri
118 | L4-007-05875 | City of Malabon University | 1-1H9KBIY | Malabon City | NCR | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 7, 2026, For AKTI checking 2025-05-09¦JCR- Site is online May 9, 2025 2025-03-05¦JGT: CMS acceptance done on March 04, 2025 - site online | AKTI | 10-Apr-2026¦Fri
119 | L4-006-00789 | Sto. Nino Elementary School | 1-1FYBHM7 | Marikina City | NCR | 7 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 7, 2026, For AKTI checking 2026-03-20¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. 2026-03-15¦RBD:Sent an email to PLDT to check for the downtime of this site and Sent Email to DICT. | AKTI | 10-Apr-2026¦Fri
120 | L4-022-05EED | Palar Health Center | 1-1H9GVZZ | Taguig City | NCR | 6 | #SLA-CMS_Down | 2026-04-10¦MFM: Site is offline since April 7, 2026, for AKTI checking 2026-04-07¦MFM: Site is now online 2026-03-31¦MFM: For AKTi site inspection and Connectivity is unstable, requesting for restarting the modem | AKTI | 10-Apr-2026¦Fri
121 | L4-005-00008 | Philippine Trade Training Center |  | Pasay City | NCR | 6 | #SLA-iGov-DownCMS | 2026-04-10¦ MFM: Site is experincing unstable connection, for AKTI checking 2026-03-14¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. 2026-03-12¦RBD:Sent an email to DICT for the downtime. | AKTI | 10-Apr-2026¦Fri
122 | L4-005-0070A | Rafael Palma Elementary School |  | Manila City | NCR | 6 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 7, 2026, For AKTI checking 2025-12-04¦Akti: Done CMS Acceptance 2025-11-26¦JCR: for CMS acceptance schedule of AKTI | AKTI | 10-Apr-2026¦Fri
123 | L4-15E-05513 | Villa Aglipay NHS | 172697159964059 | San Jose | Tarlac | 6 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 6, 2026, For AKTI checking 2026-03-26¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-03-25¦Akti: The SC turn off the power after school hours. For energy saving. | AKTI | 10-Apr-2026¦Fri
124 | L4-013-006BE | Don Galo Elementary School | 1-1G8UW7P | Parañaque City | NCR | 6 | #SLA-CMS_Down | 2026-04-13¦ MFM: Sent a message to AKTI in viber and TG for site inspection and restoration 2026-03-31¦MFM: For AKTi site inspection and Connectivity is unstable, requesting for restarting the modem 2026-03-14¦RBD:An email was sent to PLDT requesting verification of the site’s downtime and the corresponding root cause analysis (RCA).An Email was also submitted to DICT. | AKTI | 13-Apr-2026¦Mon
125 | L4-004-0068C | Almanza Elementary School - T. S. Cruz Annex | 1-1GTND1C | Las Piñas City | NCR | 6 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 8, 2026, For AKTI checking 2025-07-31¦JCR- JPC bypassed the UPS, the site now regained its connectivity 2025-07-28¦JCR: to restore - for schedule from MDS Team | AKTI | 10-Apr-2026¦Fri
126 | L4-03F-00C40 | Dona Josefa Marcos ES | 167600201668705 | Currimao | Ilocos Norte | 5 | #SLA-CMS_Down | 2026-04-07 ¦MFM: Site is offline on March 31, 2026, for AKTI checking 2026-02-23¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. 2026-02-09¦ BSV: Submitted an Email on PLDT with regards to the verification of the RCA Downtime on site. An Email was also submitted to DICT. | AKTI | 07-Apr-2026¦Tue
127 | L4-063-00A33 | Sulbec PS | 169209142847290 | Pasuquin | Ilocos Norte | 3 | #SLA-CMS_Down | 2026-04-10¦JCR- Site is offline since April 6, 2026, For AKTI checking 2026-03-18¦MFM: Done rectified, as per AKTI, They disconnect the power tapping connected to our combox because another contractor claims it is also part of the DICT project, specifically the DICT Free WiFi using Starlink ISP. Site is now online. 2026-03-06¦MFM: Sent a message in TG to Akti for restoration | AKTI | 10-Apr-2026¦Fri
128 | L4-005-0007B | Department of Justice - Manila City |  | Manila City | NCR | (New AP) | #CMS-ForTransfer | 2026-03-12¦MFM: Subejct for AKTI reco of site transfer. Igov site. 2026-02-01¦ RJA: Subejct for AKTI reco of site transfer. Igov site. Once with reco, subejct for MDS req to DICT for the installation 2026-01-18¦ RJA: As coordinated with DICT, we are to render site change / transfer for thsi site due to its extenral condition. (Extenral dependency. Site is requesting Sec to Sec letter which wil ltake up too much time and resources ) | AKTI | 12-Mar-2026¦Thu